## Slide 1: JOINOLOG - Jordan Innovation Center for Logistics
Representation on the progress of the Jordan Innovation Center for Logistics
Notes: Presented by Ismail

## Slide 2: Agenda
Introduction
Advisory Board
Project Stages
Project Team
Timeline
Future Projects
Opportunities
-What is JOINOLOG? -How it started? -Why do we need JOINOLOG? -Clustering advantages
-Who are the project team?
-Who are the members of the advisory board?
-What is the timeline for the project?
-What are the identified project stages?
-What are the future projects planned for JOINOLOG?
-Possible opportunities for JOINOLOG
Notes: Presented by Ismail

## Slide 3: Introduction
What is JOINOLOG?
The journey of the Jordan Innovation Center for Logistics started in 2018. In a Flying Faculty cooperation between Hochschule Fulda and German Jordanian University (GJU).
Objective
The overall objective of the project JOINOLOG is the conception of an innovation center for logistics in Jordan. This is intended to promote research conditions, innovation transfer and governance structures.
Focus
The focus is on collaboration through joint research projects, trainings and events, exchange of content and promotion of innovation in logistics.
Future
The center‘s orientation will be vital to its sustainability. Ultimately, an institution is planned for this purpose, which brings together all logistics-related actors in the country and beyond, thus offering them a platform for sustainable collaboration.
Notes: Presented by Ismail

## Slide 4: How JOINOLOG started
How did we start JOINOLOG?
It started in 2018 when both universities collaborated after noticing the lack of innovation in the logistical sector in Jordan. The idea was granted funding by the German Federal Ministry of Education and Research for the preparation stage to check the feasibility and sustainability of such an idea in the Jordanian landscape and the implementation stage that has begun in February 2021 which will last until January 2024.
Why did we start JOINOLOG?
The various challenges in the current logistics system in Jordan.
The world’s bank logistics index for Jordan reflected that there is an immense room for improvement.
The well-built IT infrastructure in Jordan.
The willingness of the government to support the logistics sector.

## Slide 5: Why do we need JOINOLOG? Clustering Creating a Network Developing Opportunites Research development
Through JOINOLOG new opportunites are created for the future of logisitcs and supply chain.
Knowledge sharing through clustering is one of the biggest advantages that JOINOLOG will provide to the Jordanian market.
JOINOLOG aims to create a network connecting all vital players in the field of logistics and supply chain in Jordan.
Research regarding current logistical challenges and opportunities and knowledge generation is a big part of the work under JOINOLOG.

## Slide 6: Clustering Advantages:
Clustering is a critical business aspect for JOINOLOG that would:
Improve research conditions and innovation transfer.
Create a collaborative environment with the necessary conditions and governance structures that enable members of the network to collaborate.
Build the basis and the network for vital players from logistics, supply chain and governmental parties to enable them to work in an interdisciplinary and cross-sectoral manner in order to create added value for all parties.
Utilize different events such as cluster meetings, expert discussions, annual conferences and lectures to impart knowledge, increase the cluster members' orientation and the beneficial reputation of clusters.

## Slide 7: Project Team
Dr.
Ismail Abushaikha
Ismail.Abushaikha@gju.edu.jo
Rana Badran
Rana.Badran@gju.edu.jo
Jakob Grubmüller
Jakob.Grubmueller@w.hs-fulda.de
Sascha Düerkop
Sascha.Dueerkop@w.hs-fulda.de
Prof. Dr.
Michael Huth
Michael.Huth@w.hs-fulda.de
Notes: Presented by Ismail

## Slide 8: Advisory Board
What is PAB?
The Project Advisory Board steers the project into the right direction. For the next three years, the board makes important decisions about the structure, focus and future of JOINOLOG. The key partners of the past project phase are invited to be part of the board. They form the most influential group of the project’s coming implementation.
Structure
The project managers from HFD and GJU will consult the board regarding the structure of the center.
Focus
The PAB will set the center‘s focus. What themes will be researched on in projects, which trainings will be conducted, what kind of output is desired? These questions will be answered by the project management and PAB.
Future
The center‘s orientation will be vital to its sustainability. The advisory board can influence the ways in which JOINOLOG will continue to exist after the period of funding by BMBF.
23/09/2021
Notes: Presented by Ismail

## Slide 9: Advisory Board
The following professionals have been part of the JOINOLOG Advisory Board since its foundation in May 2021.
Hakam Abul Feilat, representing AQABA Logistics Village (ALV)
Dr. Mahmoud Abuhussein, representing The Higher Council for Science and Technology (HCST)
Notes: Presented by Ismail

## Slide 10: Advisory Board
Fares L. Abudayyeh, representing the Ministry of Transport.
Martin Ohlsen, former Logistics Director of the World Food Programme
Notes: Presented by Ismail

## Slide 11: Timeline
Work packages for 2021:
Notes: Presented by Ismail

## Slide 12: Timeline
Work packages for 2022:
Notes: Presented by Ismail

## Slide 13: Timeline
Work packages for 2023:
Notes: Presented by Ismail

## Slide 14: Timeline
Work package for 2024:
Notes: Presented by Ismail

## Slide 15
Identification and analysis of funding opportunities
Milestone achieved: Funding Strategy
Research Workshop
Milestone:
Physical workshop in November.
Work Package 140
Research WP1: Research Centers as Knowledge Hubs
Milestone achieved:
Risk Management Report
Work Package 130
Designing and setting-up the scientific network
Milestone achieved:
Partnership Strategy
Work Package 110
Exploration of Implementation Forms
Milestone:
Implementation strategy (To be covered in upcoming workshop)
Work Package 210
23/09/2021
Work Package 220
Modeling of Cooperational Opportunities
Milestone:
Cooperation strategy. (To be covered in upcoming workshop)
Work Package 120
Project Stages 2021

## Slide 16
Capacity Building
Milestone: Initial preparation for trainings
Specification of Internal Processes
Milestone:
Process map
Work Package 310
Finalization of Research Roadmap
Milestone:
Research strategy
Work Package 250
Derivation of Center Output Milestone: Prioritisation system
Work Package 230
Developing of Organizational Structure
Milestone:
Organizational structure
Work Package 320
23/09/2021
Work Package 330
Developing of Training Concepts
Milestone:
Training concept
Work Package 240
Project Stages 2022

## Slide 17
Introduction Event
Mileston: Preparation and Readiness of Concept for Introduction Event
Development of Scientific Concepts for Center Sustainability
Milestone:
Development of scientific concept for the sustainability of the center
Work Package 410
Development Business Continuation Concept
Milestone:
Sustainable financing secured
Work Package 360
Definition of Research Projects
Mileston: Definition of Research Projects and Questions
Work Package 340
Hand-Over Report
Milestone:
Preparation of Hand-Over Report
Work Package 420
23/09/2021
Work Package 350
Project Stages 2023

## Slide 18
Research WP2: Pilot Research Project
Milestone achieved: First research project carried out within the framework of JOINOLOG
Project Management / Coordination
Work Package 700
Trainings
Milestone: Field report and outlook on trainings
Work Package 500
23/09/2021
Work Package 600
Project Stages 2024

## Slide 19: Workshop Partenrship Website Hackathon
An official website to be published for JOINOLOG to cover a newsletter, blogs and updates.
A Hackathon is scheduled to be held during 2022 that highlights supply chain challenges in the field.
A workshop will be held in Amman, Jordan with the German project team and the board of advisory.
Partnership mapping is being undertaken to search for suitable future partners for JOINOLOG.
Future Projects

## Slide 20: Opportunities
There are many utilization opportunities for JOINOLOG. These include similar innovation centers. E.g: HOLM
Possible Opportunities can be:
Knowledge sharing.
Partnership opportunity.
Collaboration in events and workshops.
Collaboration on research papers.
Notes: Presented by Ismail

## Slide 21: Opportunities
There are many utilization opportunities for JOINOLOG with the network of German partner universities and the German Jordanian University.
Possible Opportunities can be:
JOINOLOG can act as a mediator between the German universities, the German Jordanian University and companies in Jordan.
JOINOLOG can be a source for information on the logistical situation in Jordan.
Internship opportunity for students at JOINOLOG.
Collaboration on research papers.
German Partner Universities
Notes: Presented by Ismail

## Slide 22: Opportunities
There are many utilization opportunities for JOINOLOG with the network of German partner universities and the German Jordanian University.
Possible Opportunities can be:
JOINOLOG can act as a mediator between the German universities, the German Jordanian University and companies in Jordan.
JOINOLOG can be a source for information on the logistical situation in Jordan.
Internship opportunity for students at JOINOLOG.
Collaboration on research papers.
German Partner Universities
Notes: Presented by Ismail

## Slide 23: Thank you
Dr.
Ismail Abushaikha
Ismail.Abushaikha@gju.edu.jo
شكراً جزيلاً
Vielen Dank
23/09/2021
Notes: Presented by Michael